## Sheet1
MultiBrowser
* My Email Address:tomas19860629@gmail.com
* Estimated time:8 weeks
* Prepay:500USD
| Dev Language | Period | Week | Task | Budget($)
Desktop App | Java | 5 weeks | 1 | Main Project Structure Login Dialog Login License Invalid Dialog | 500
|  |  | 2 | Tree Function In Java Fucntions In "New" Menu | 500
License Serve | PHP | 3 weeks
|  |  | 3 | Fucntions In "Action" Menu Fucntions In "Setting" Menu Fucntions In "Help" Menu | 500
|  |  | 4 | Import Function | 500
|  |  | 5 | License Function In Profile register(Get MAC, IP Address) | 500
|  |  | 6 | License Server | 500
|  |  | 7 | Wordpress PlugIn | 500
|  |  | 8 | Other(I will fix and modify according to client`s requirements) | 1000
5000