## Sheet1
MultiBrowser
* My Email Address:tomas19860629@gmail.com
* Estimated time:8 weeks
* Prepay:500USD
| Dev Language | Period | Week | Task | Budget($)
Desktop App | Java | 8 weeks | 1 | Main Project Structure Login Dialog Login License Invalid Dialog | $500 PAID 5th june + $500 paid in advance 29 May
|  |  | 2 | Tree Function In Java Fucntions In "New" Menu | $500 PAID 12-6-20
License Serve | PHP | 3 weeks
|  |  | 3 | Fucntions In "Action" Menu Fucntions In "Setting" Menu Fucntions In "Help" Menu | 500 PAID 19-06-20
|  |  | 4 | Import Function | 500 PAID 26-06-20
|  |  | 5 | License Function In Profile register(Get MAC, IP Address) | 500 PAID 04-07-2020
|  |  | 6 | License Server | 500 PAID 13-07-2020
|  |  | 7 | License Server and Keygen + Research | 500 PAID 17-07-2020
|  |  | 8 | Add user agent switcher (default UA is correct one) or setting for random UA. Fix bugs and apply design when document 1 is sent, Do encryption for backup download and upload to 7zip encrypted file. To prevent mysql injection. Add profile report when design is sent. | 500
|  |  | 9 | More design fixes, any feature updates or changes and more bug testing. I build Wp website with woocommerce with license options and prices. I build server to host the java application so we can test. Apply logo graphics and software icon I supply. Install and test the application in server environment
500
|  |  | 10 | Wordpress PlugIn and integration, more server setup and tests. | 500
|  |  | 11 | Other(I will fix and modify according to client`s requirements). This will be feature tests. Bug fixes. Server and live tests. And more | 1000
6500

## Sheet2
Outstanding tasks
bug fixing
Ips to profile doesn’t work
Test new browser and tweak jfx
Add gfx where required